## Sheet1
Project Title
PCIe Windows Driver / Received and Transmit Data From/To PCIe Device
Project Manager | Nathaniel Fernandez , Ashraful, Moazzem Hossain
Author | Nathaniel Fernandez
Client | ASA Microsystems
Date Submitted | 1/24/2022
Project Goal | To be able to transmit/receive simple DATA from PCIe Host to arria 10 fpga (risk-v) device
Schedule
Host Side
Tasks | Num of Hrs | Due Date | Days | Task Description
PCIEe Windows Driver
Download Right Win Ver | 8 | 1/25/2022 - 1/25/2022 | Tue | Download the right Intel PCIe Windows Driver
Testing | 16 | 1/26/2022 - 1/27/2022 | Wed-Thu | Test the Downloaded Windows Driver
Host PCIe Application
Coding
QT Windows App (Front) | 16 | 1/28/2022 - 1/31/2022 | Fri-Mon | Use QT as Front End for Simple UI for transmit and receive data
Transmit Data | 8 | 2/1/2022 - 2/1/2022 | Tue | Use QT to transmit data
Receive Data | 8 | 2/2/2022 - 2/2/2022 | Wed | Use QT to receive data
Back-End
Transmit Data | 8 | 2/3/2022 - 2/3/2022 | Thu | Back-End transmit data to PCIe device
Receive Data | 8 | 2/4/2022 - 2/4/2022 | Fri | Back-End receive data from PCIe device
Testing
Front-End | 16 | 2/7/2022 - 2/8/2022 | Mon-Tue | Test QT Front-End Transmit/Receive
Back-End | 16 | 2/9/2022 - 2/10/2022 | Wed-Thu | Test QT Back-End Transmit/Receive
Host Hrs | 104
Device Side
Coding
BIOS
Bootup | 2 | 2/11/2022 - 2/11/2022 | Fri | Write Firmware Code for Boot-up
Linker Directives | 2 |  |  | Write Firmware Code for Linker Directives
Memory Allocation | 4 |  |  | Write Firmware Code for Generic Memory Allocation
DDR4 Access | 4 | 2/14/2022 - 2/14/2022 | Mon | Write Firmware Code for DDR4 Access
Icache/Dcache Init | 4
PLL/CLK Init | 4 | 2/15/2022 - 2/16/2022 | Tue-Wed
Peripheral Init | 4
DMA | 4 | 2/17/2022 - 2/17/2022 | Thu
Main App | 16 | 2/18/2022 - 2/18/2022 | Fri | Write Main Firmware Application
PCIe
Initialization | 8 | 2/21/2022 - 2/21/2022 | Mon
Transmit | 4 | 2/22/2022 - 2/22/2022 | Tue
Receive | 4
Testing
Tools Setup
Compiler, Debugger | 6 | 2/23/2022 - 2/23/2022 | Wed | Setup Compiler, Debugger for Firmware Coding and Testing
In-Circuit Emulator | 2
BIOS
Bootup | 2 | 2/24/2022 - 2/24/2022 | Thu
Linker Directives | 2
Memory Allocation | 4
DDR4 Access | 4 | 2/25/2022 - 2/28/2022 | Fri-Mon
Icache/Dcache Init | 4
PLL/CLK Init | 4 | 3/1/2022 - 3/1/2022 | Tue
Peripheral Init | 4
DMA | 4 | 3/2/2022 - 3/2/2022 | Wed
Main App | 16 | 3/3/2022 - 3/3/2022 | Thu
PCIe
Initialization | 8 | 3/4/2022 - 3/4/2022 | Fri
Transmit | 4 | 3/5/2022 - 3/5/2022 | Thu
Receive | 4
Device Hrs | 128
Host and Device Total Hours | 232